## SPRINT #1 224 - 36
SCRUM Master: Franklin Schneider
Completed Task List |  |  |  |  | Meeting List (Differs from originally planned meetings)
Date | Team Member(s) | Task Completed | Time Spent | FR | Date | Added or Removed | Team Member(s) | Purpose | Time Spent
2020-02-25 | Ryan/Frank | Web API project created w/ entity framework user authentication | 1 hr | 1&9
2020-02-27 | Ryan/Frank | Configure Swagger API documentation/wrote algorithm to fetch API viewModel classes on startup | 3 hr | 1&9
2020-02-29 | Ryan/Frank | Practice w/ WPF front end design (basics of binding params to front end), basics of caliburn.micro, etc... | 2 hr | 1&9
2020-03-02 | Ryan/Frank | Initial log in WPF form created | 1 hr | 1&9
2020-03-04 | Ryan | More login form creation - began figuring out how to connect w/ the API and EF user DB | 5 hr | 1&9
2020-03-05 | Ryan | Successfully connected the form w/ API - basic error checking | 4 hr | 1&9
2020-03-05 | Tyler/Stephen | WPF Front end developement and user interface | 6 hr | 2&3
2020-03-05 | Tyler/Stephen | WPF Research and Practice | 7 hr | 2&3

## SPRINT #2
Completed Task List |  |  |  | Meeting List (Differs from originally planned meetings)
Date | Team Member(s) | Task Completed | Time Spent | Date | Added or Removed | Team Member(s) | Purpose | Time Spent

## SPRINT #3
Completed Task List |  |  |  | Meeting List (Differs from originally planned meetings)
Date | Team Member(s) | Task Completed | Time Spent | Date | Added or Removed | Team Member(s) | Purpose | Time Spent

## SPRINT #4
Completed Task List |  |  |  | Meeting List (Differs from originally planned meetings)
Date | Team Member(s) | Task Completed | Time Spent | Date | Added or Removed | Team Member(s) | Purpose | Time Spent